## NCR_Data
NCR ID | Date Raised | Vessel | System Category | Severity | Description | Root Cause Category | Assigned Dept | Target Date | Date Closed | Days to Close | Status | Month | System Category List | Severity List | Status List
NCR-2023-001 | 2023-11-28 | MV Stellamare | HVAC | Minor | Ventilation fan belt worn | Equipment Failure | Deck | 2023-12-05 |  |  | Open | Nov | HVAC | Minor | Open
NCR-2023-002 | 2023-10-11 | MV Stellamare | Cargo Equipment | Major | Crane wire certification expired | Human Error | Deck | 2023-10-25 | 2023-10-15 | 4 | In Progress | Oct | Cargo Equipment | Major | In Progress
NCR-2023-003 | 2023-10-19 | MV Trent | Machinery | Minor | Aux engine governor hunting | Equipment Failure | External Contractor | 2023-11-18 |  |  | In Progress | Oct | Machinery | Critical | Closed
NCR-2023-004 | 2023-01-08 | MV Trent | Machinery | Major | F/O separator alarm fault | Equipment Failure | Deck | 2023-02-07 | 2023-02-04 | 27 | Closed | Jan | Structural |  | Overdue
NCR-2023-005 | 2023-02-23 | MV Frisian Summer | Structural | Major | Accommodation ladder net torn | Human Error | External Contractor | 2023-03-02 |  |  | In Progress | Feb | Navigation Equip.
NCR-2023-006 | 2023-07-17 | MV Stellamare | Cargo Equipment | Major | Cargo pump cavitation | External Factor | Deck | 2023-07-24 | 2023-08-03 | 17 | Closed | Jul | Safety Equipment
NCR-2023-007 | 2023-06-02 | MV Stellamare | Structural | Major | Deck coating deterioration | Maintenance Overdue | Shore Management | 2023-08-01 |  |  | Open | Jun | Electrical
NCR-2023-008 | 2023-07-10 | MV Trent | Navigation Equip. | Major | AIS transponder dropout | Design Defect | Engineering | 2023-07-24 | 2023-07-28 | 18 | Closed | Jul
NCR-2023-009 | 2023-03-29 | MV Flinterborg | Safety Equipment | Major | Fire extinguisher pressure low | Design Defect | Shore Management | 2023-04-05 | 2023-04-03 | 5 | Closed | Mar
NCR-2023-010 | 2023-06-15 | MV Flinterborg | Navigation Equip. | Critical | AIS transponder dropout | Equipment Failure | External Contractor | 2023-08-14 |  |  | In Progress | Jun
NCR-2023-011 | 2023-11-30 | MV Flinterborg | Electrical | Major | Navigation light outage | Design Defect | Catering | 2023-12-30 |  |  | Open | Nov
NCR-2023-012 | 2023-08-12 | MV Calypso | Safety Equipment | Major | Fire extinguisher pressure low | External Factor | External Contractor | 2023-08-19 |  |  | In Progress | Aug
NCR-2023-013 | 2023-03-02 | MV Trent | Machinery | Major | Aux engine governor hunting | External Factor | Engineering | 2023-05-01 | 2023-04-03 | 32 | Closed | Mar
NCR-2023-014 | 2023-10-02 | MV Frisian Summer | Cargo Equipment | Minor | Crane wire certification expired | Design Defect | Engineering | 2023-11-01 |  |  | In Progress | Oct
NCR-2023-015 | 2023-06-28 | MV Stellamare | Navigation Equip. | Major | Gyrocompass deviation exceeds spec | Human Error | Shore Management | 2023-07-12 | 2023-07-07 | 9 | Closed | Jun
NCR-2023-016 | 2023-11-21 | MV Frisian Summer | Structural | Critical | Handrail corroded at Fr.42 | Equipment Failure | Shore Management | 2023-12-05 | 2023-12-27 | 36 | Closed | Nov
NCR-2023-017 | 2023-01-05 | MV Calypso | Navigation Equip. | Major | Radar antenna bearing worn | Procedure Gap | Shore Management | 2023-01-19 | 2023-02-13 | 39 | Closed | Jan
NCR-2023-018 | 2023-02-14 | MV Stellamare | Machinery | Major | Main engine turbocharger surge | External Factor | Deck | 2023-02-28 |  |  | Open | Feb
NCR-2023-019 | 2023-10-13 | MV Trent | Navigation Equip. | Major | Gyrocompass deviation exceeds spec | Equipment Failure | Catering | 2023-10-27 |  |  | Open | Oct
NCR-2023-020 | 2023-07-28 | MV Frisian Summer | Safety Equipment | Minor | Immersion suit zip defective | Human Error | Deck | 2023-08-11 | 2023-08-01 | 4 | Closed | Jul
NCR-2023-021 | 2023-11-02 | MV Calypso | Electrical | Minor | Emergency generator test failure | Human Error | Engineering | 2023-11-16 | 2023-11-07 | 5 | Closed | Nov
NCR-2023-022 | 2023-06-23 | MV Stellamare | Cargo Equipment | Major | Derrick block sheave worn | Equipment Failure | Catering | 2023-07-07 |  |  | Open | Jun
NCR-2023-023 | 2023-10-24 | MV Calypso | Safety Equipment | Major | Immersion suit zip defective | Maintenance Overdue | Deck | 2023-10-31 | 2023-11-23 | 30 | Closed | Oct
NCR-2023-024 | 2023-07-05 | MV Flinterborg | Safety Equipment | Major | Life jacket light battery expired | Design Defect | Engineering | 2023-07-12 | 2023-07-29 | 24 | Closed | Jul
NCR-2023-025 | 2023-03-01 | MV Trent | Electrical | Major | Battery bank below threshold | Equipment Failure | External Contractor | 2023-03-15 | 2023-03-19 | 18 | Closed | Mar
NCR-2023-026 | 2023-02-12 | MV Flinterborg | Structural | Minor | Deck coating deterioration | Human Error | Catering | 2023-02-19 |  |  | Overdue | Feb
NCR-2023-027 | 2023-05-06 | MV Trent | Safety Equipment | Major | Fire extinguisher pressure low | Maintenance Overdue | Engineering | 2023-05-20 | 2023-06-02 | 27 | Closed | May
NCR-2023-028 | 2023-05-20 | MV Flinterborg | Navigation Equip. | Major | Gyrocompass deviation exceeds spec | Equipment Failure | Deck | 2023-06-19 | 2023-05-26 | 6 | Closed | May
NCR-2023-029 | 2023-10-28 | MV Calypso | HVAC | Minor | AC compressor failure – accommodation | Human Error | Catering | 2023-12-27 | 2023-12-03 | 36 | Closed | Oct
NCR-2023-030 | 2023-03-26 | MV Stellamare | Cargo Equipment | Minor | Hatch cover seal damaged | Human Error | Catering | 2023-04-02 |  |  | Open | Mar
NCR-2023-031 | 2023-05-05 | MV Flinterborg | HVAC | Minor | Ventilation fan belt worn | External Factor | Catering | 2023-05-12 |  |  | Open | May
NCR-2023-032 | 2023-08-07 | MV Calypso | Cargo Equipment | Major | Cargo pump cavitation | Equipment Failure | Shore Management | 2023-08-21 | 2023-08-18 | 11 | Closed | Aug
NCR-2023-033 | 2023-12-14 | MV Frisian Summer | Safety Equipment | Major | Life jacket light battery expired | Human Error | External Contractor | 2023-12-21 | 2023-12-30 | 16 | Closed | Dec
NCR-2023-034 | 2023-09-21 | MV Frisian Summer | Electrical | Minor | Emergency generator test failure | Equipment Failure | Shore Management | 2023-10-21 | 2023-10-28 | 37 | Closed | Sep
NCR-2023-035 | 2023-06-08 | MV Calypso | Structural | Minor | Deck coating deterioration | Design Defect | Catering | 2023-07-08 |  |  | Overdue | Jun
NCR-2023-036 | 2023-02-27 | MV Trent | Navigation Equip. | Critical | Radar antenna bearing worn | Design Defect | Catering | 2023-03-13 | 2023-04-09 | 41 | Closed | Feb
NCR-2023-037 | 2023-04-22 | MV Frisian Summer | Electrical | Minor | Shore power connection fault | External Factor | External Contractor | 2023-05-22 |  |  | Overdue | Apr
NCR-2023-038 | 2023-01-31 | MV Stellamare | Machinery | Major | F/O separator alarm fault | Human Error | Engineering | 2023-03-02 |  |  | In Progress | Jan
NCR-2023-039 | 2023-11-27 | MV Frisian Summer | Electrical | Minor | Battery bank below threshold | External Factor | Engineering | 2023-12-04 | 2023-12-09 | 12 | Closed | Nov
NCR-2023-040 | 2023-10-11 | MV Stellamare | Structural | Major | Handrail corroded at Fr.42 | Maintenance Overdue | Deck | 2023-10-18 | 2023-10-16 | 5 | Closed | Oct
NCR-2023-041 | 2023-07-07 | MV Trent | Machinery | Major | Main engine turbocharger surge | Procedure Gap | Catering | 2023-09-05 |  |  | Overdue | Jul
NCR-2023-042 | 2023-03-25 | MV Trent | Structural | Major | Handrail corroded at Fr.42 | Maintenance Overdue | Engineering | 2023-04-08 |  |  | Open | Mar
NCR-2023-043 | 2023-06-24 | MV Flinterborg | Structural | Minor | Handrail corroded at Fr.42 | Procedure Gap | Deck | 2023-07-01 | 2023-06-29 | 5 | Closed | Jun
NCR-2023-044 | 2023-09-02 | MV Trent | Electrical | Minor | Battery bank below threshold | Procedure Gap | Shore Management | 2023-09-16 | 2023-10-17 | 45 | Closed | Sep
NCR-2023-045 | 2023-04-13 | MV Flinterborg | Navigation Equip. | Major | Radar antenna bearing worn | Procedure Gap | Shore Management | 2023-06-12 |  |  | Open | Apr
NCR-2023-046 | 2023-10-06 | MV Frisian Summer | HVAC | Critical | Reefer plant temp deviation | Equipment Failure | Catering | 2023-11-05 | 2023-11-16 | 41 | Closed | Oct
NCR-2023-047 | 2023-08-15 | MV Frisian Summer | Machinery | Minor | Aux engine governor hunting | External Factor | Catering | 2023-08-22 | 2023-09-23 | 39 | Closed | Aug
NCR-2023-048 | 2023-04-12 | MV Frisian Summer | HVAC | Minor | AC compressor failure – accommodation | External Factor | Catering | 2023-04-26 | 2023-04-19 | 7 | Closed | Apr
NCR-2023-049 | 2023-12-11 | MV Frisian Summer | Cargo Equipment | Major | Crane wire certification expired | Design Defect | Shore Management | 2024-01-10 |  |  | Open | Dec
NCR-2023-050 | 2023-06-21 | MV Flinterborg | Machinery | Major | Bilge pump non-operational | Equipment Failure | External Contractor | 2023-08-20 |  |  | Open | Jun
NCR-2023-051 | 2023-04-04 | MV Calypso | Cargo Equipment | Major | Crane wire certification expired | Procedure Gap | Shore Management | 2023-04-18 | 2023-05-14 | 40 | Closed | Apr
NCR-2023-052 | 2023-11-11 | MV Frisian Summer | Safety Equipment | Major | Fire extinguisher pressure low | External Factor | External Contractor | 2023-11-25 |  |  | Open | Nov
NCR-2023-053 | 2023-05-30 | MV Calypso | Machinery | Minor | F/O separator alarm fault | Human Error | Deck | 2023-06-29 | 2023-06-14 | 15 | Closed | May
NCR-2023-054 | 2023-03-21 | MV Stellamare | HVAC | Major | AHU filter blocked | External Factor | Engineering | 2023-05-20 | 2023-05-03 | 43 | Closed | Mar
NCR-2023-055 | 2023-10-26 | MV Trent | Machinery | Minor | Aux engine governor hunting | Maintenance Overdue | Deck | 2023-11-09 |  |  | Open | Oct
NCR-2023-056 | 2023-01-07 | MV Stellamare | Structural | Major | Handrail corroded at Fr.42 | Design Defect | Catering | 2023-03-08 | 2023-01-25 | 18 | Closed | Jan
NCR-2023-057 | 2023-03-08 | MV Flinterborg | Electrical | Minor | Shore power connection fault | Maintenance Overdue | Catering | 2023-05-07 |  |  | In Progress | Mar
NCR-2023-058 | 2023-10-12 | MV Flinterborg | Electrical | Minor | Battery bank below threshold | Maintenance Overdue | Shore Management | 2023-10-26 |  |  | In Progress | Oct
NCR-2023-059 | 2023-05-26 | MV Calypso | Safety Equipment | Minor | EPIRB registration lapsed | Maintenance Overdue | Engineering | 2023-06-25 | 2023-06-19 | 24 | Closed | May
NCR-2023-060 | 2023-06-17 | MV Calypso | HVAC | Critical | Ventilation fan belt worn | Maintenance Overdue | Deck | 2023-07-01 | 2023-07-16 | 29 | Closed | Jun
NCR-2023-061 | 2023-06-23 | MV Calypso | Safety Equipment | Major | Fire extinguisher pressure low | Maintenance Overdue | External Contractor | 2023-06-30 |  |  | In Progress | Jun
NCR-2023-062 | 2023-10-26 | MV Flinterborg | Safety Equipment | Critical | EPIRB registration lapsed | Procedure Gap | External Contractor | 2023-12-25 | 2023-12-02 | 37 | Closed | Oct
NCR-2023-063 | 2023-11-09 | MV Trent | Safety Equipment | Major | Immersion suit zip defective | Maintenance Overdue | Engineering | 2024-01-08 | 2023-12-07 | 28 | Closed | Nov
NCR-2023-064 | 2023-03-30 | MV Flinterborg | Electrical | Minor | Emergency generator test failure | Maintenance Overdue | Catering | 2023-04-06 | 2023-04-29 | 30 | Closed | Mar
NCR-2023-065 | 2023-03-15 | MV Flinterborg | Electrical | Critical | Battery bank below threshold | Procedure Gap | Deck | 2023-05-14 | 2023-04-11 | 27 | Closed | Mar

## KPI_Summary
ISM Non-Conformity Report — Quality KPI Summary 2023
Fleet: Royal Wagenborg B.V. (The Netherlands) ¦ Period: January – December 2023 ¦ Vessels: 5
KEY PERFORMANCE INDICATORS
Total NCRs Raised |  | Closed NCRs |  | Open NCRs |  | Overdue NCRs
65 |  | 37 |  | 14 |  | 4
Closure Rate |  | Avg Days to Close |  | Critical NCRs |  | In Progress
56.92% |  | 23.3421 |  | 7 |  | 10
[8 empty] | Severity | Count | Status | Count
NCR BREAKDOWN BY SYSTEM CATEGORY | [7 empty] | Critical | 7 | Closed | 37
System Category | Total NCRs | Critical | Major | Minor | Closed | Overdue | Closure Rate | Major | 35 | Open | 14
HVAC | 7 | 2 | 1 | 4 | 5 | 0 | 71.43% | Minor | 23 | In Progress | 10
Electrical | 11 | 1 | 2 | 8 | 7 | 1 | 63.64% |  |  | Overdue | 4
Navigation Equip. | 8 | 2 | 6 | 0 | 5 | 0 | 62.5% | Assigned Dept | NCR Count
Safety Equipment | 12 | 1 | 9 | 2 | 9 | 0 | 75% | Deck | 14
Cargo Equipment | 8 | 0 | 6 | 2 | 3 | 0 | 37.5% | External Contractor | 11
Machinery | 10 | 0 | 6 | 4 | 4 | 1 | 40% | Shore Management | 12
Structural | 9 | 1 | 5 | 3 | 4 | 2 | 44.44% | Engineering | 12
TOTAL | 65 | 7 | 35 | 23 | 37 | 4 | 56.92% | Catering | 16

## Trend_Analysis
NCR Trend & Root Cause Analysis — 2023
Month | Total NCRs | Critical | Closed | Root Cause Category | Count
Jan | 4 | 0 | 3 | Human Error | 11
Feb | 4 | 1 | 1 | Equipment Failure | 13
Mar | 9 | 1 | 6 | Procedure Gap | 8
Apr | 4 | 0 | 2 | Maintenance Overdue | 13
May | 5 | 0 | 4 | External Factor | 11
Jun | 9 | 2 | 3 | Design Defect | 9
Jul | 5 | 0 | 4
Aug | 3 | 0 | 2
Sep | 2 | 0 | 2
Oct | 11 | 2 | 5
Nov | 7 | 1 | 4
Dec | 2 | 0 | 1

## CAPA_Tracker
CAPA Tracker — Open / In Progress / Overdue Non-Conformities
Corrective & Preventive Actions requiring follow-up. This list is LIVE — it auto-updates from NCR_Data (FILTER + XLOOKUP), sorted by most urgent Target Date first.
NCR ID | Vessel | System | Severity | Description | Target Date | Status
NCR-2023-026 | MV Flinterborg | Structural | Minor | Deck coating deterioration | 2023-02-19 | Overdue
NCR-2023-018 | MV Stellamare | Machinery | Major | Main engine turbocharger surge | 2023-02-28 | Open
NCR-2023-005 | MV Frisian Summer | Structural | Major | Accommodation ladder net torn | 2023-03-02 | In Progress
NCR-2023-038 | MV Stellamare | Machinery | Major | F/O separator alarm fault | 2023-03-02 | In Progress
NCR-2023-030 | MV Stellamare | Cargo Equipment | Minor | Hatch cover seal damaged | 2023-04-02 | Open
NCR-2023-042 | MV Trent | Structural | Major | Handrail corroded at Fr.42 | 2023-04-08 | Open
NCR-2023-057 | MV Flinterborg | Electrical | Minor | Shore power connection fault | 2023-05-07 | In Progress
NCR-2023-031 | MV Flinterborg | HVAC | Minor | Ventilation fan belt worn | 2023-05-12 | Open
NCR-2023-037 | MV Frisian Summer | Electrical | Minor | Shore power connection fault | 2023-05-22 | Overdue
NCR-2023-045 | MV Flinterborg | Navigation Equip. | Major | Radar antenna bearing worn | 2023-06-12 | Open
NCR-2023-061 | MV Calypso | Safety Equipment | Major | Fire extinguisher pressure low | 2023-06-30 | In Progress
NCR-2023-022 | MV Stellamare | Cargo Equipment | Major | Derrick block sheave worn | 2023-07-07 | Open
NCR-2023-035 | MV Calypso | Structural | Minor | Deck coating deterioration | 2023-07-08 | Overdue
NCR-2023-007 | MV Stellamare | Structural | Major | Deck coating deterioration | 2023-08-01 | Open
NCR-2023-010 | MV Flinterborg | Navigation Equip. | Critical | AIS transponder dropout | 2023-08-14 | In Progress
NCR-2023-012 | MV Calypso | Safety Equipment | Major | Fire extinguisher pressure low | 2023-08-19 | In Progress
NCR-2023-050 | MV Flinterborg | Machinery | Major | Bilge pump non-operational | 2023-08-20 | Open
NCR-2023-041 | MV Trent | Machinery | Major | Main engine turbocharger surge | 2023-09-05 | Overdue
NCR-2023-002 | MV Stellamare | Cargo Equipment | Major | Crane wire certification expired | 2023-10-25 | In Progress
NCR-2023-058 | MV Flinterborg | Electrical | Minor | Battery bank below threshold | 2023-10-26 | In Progress
NCR-2023-019 | MV Trent | Navigation Equip. | Major | Gyrocompass deviation exceeds spec | 2023-10-27 | Open
NCR-2023-014 | MV Frisian Summer | Cargo Equipment | Minor | Crane wire certification expired | 2023-11-01 | In Progress
NCR-2023-055 | MV Trent | Machinery | Minor | Aux engine governor hunting | 2023-11-09 | Open
NCR-2023-003 | MV Trent | Machinery | Minor | Aux engine governor hunting | 2023-11-18 | In Progress
NCR-2023-052 | MV Frisian Summer | Safety Equipment | Major | Fire extinguisher pressure low | 2023-11-25 | Open
NCR-2023-001 | MV Stellamare | HVAC | Minor | Ventilation fan belt worn | 2023-12-05 | Open
NCR-2023-011 | MV Flinterborg | Electrical | Major | Navigation light outage | 2023-12-30 | Open
NCR-2023-049 | MV Frisian Summer | Cargo Equipment | Major | Crane wire certification expired | 2024-01-10 | Open
Formulas:
Target Date = IF([NCR ID]="","",XLOOKUP([NCR ID],tbl_NCR_Data[NCR ID],tbl_NCR_Data[Target Date]))

## Pivot_Analysis
NCR Pivot Analysis — Built with Native PivotTables
Compare these PivotTables to the COUNTIFS-based breakdown on KPI_Summary — same numbers, built a completely different way.
Pivot 1: NCR Count by System Category × Severity |  |  |  |  | Pivot 2: NCR Count by Vessel × Status
Count of NCR ID | Column Labels |  |  |  | Count of NCR ID | Column Labels
Row Labels | Critical | Major | Minor | Grand Total | Row Labels | Closed | In Progress | Open | Overdue | Grand Total
Cargo Equipment | 1 | 1 |  | 2 | MV Calypso | 9 | 2 |  | 1 | 12
Electrical |  | 1 | 2 | 3 | MV Flinterborg | 7 | 3 | 4 | 1 | 15
HVAC | 1 |  | 3 | 4 | MV Frisian Summer | 8 | 1 | 2 | 2 | 13
Machinery |  | 1 | 1 | 2 | MV Stellamare | 6 | 1 | 5 |  | 12
Navigation Equip. | 1 | 1 |  | 2 | MV Trent | 8 | 1 | 3 | 1 | 13
Structural |  | 1 | 2 | 3 | Grand Total | 38 | 8 | 14 | 5 | 65
Grand Total | 3 | 5 | 8 | 16
Pivot 3: Root Cause Category — Count & Avg Days to Close
Row Labels | Count of NCR ID | Average of Days to Close
Design Defect | 9 | 21.2
Equipment Failure | 13 | 25.1429
External Factor | 11 | 25
Human Error | 11 | 12.7143
Maintenance Overdue | 13 | 24.7143
Procedure Gap | 8 | 32.1667
Grand Total | 65 | 23.3421
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.